Local Firefighters Pension Board

Friday, 9 October 2020 at 2pm

Zoom Meeting

| Attendees: Board Members: |  |
| --- | --- |
| DCFO Craig Parkin – Employer Representative (CP) |  |
| Mark Stilwell (FBU) (Chair)–Employee Representative (MS) Cllr Sybil Fielding – Employer Representative (SF) Bryn Coleman – Employee Representative (BC) Steve Tucker (FBU) – Employee Representative (ST) |  |
| Board Advisers |  |
| Becky Smeathers – Scheme Manager (BS) Nick Linthwaite – HR Adviser (NL) Elena Johnston – Assistant Scheme Administrator (EJ) Helen Scargill – Scheme Administrator (HS) Yunus Gajra – (YG) |  |

| Agenda Item | Commentary | Outcome | Decision log. Action . . . |  |
| --- | --- | --- | --- | --- |
|  |  |  | By Whom | By When |
| 1 | Declarations of Potential Conflicts of Interest |  |  |  |
|  | Nil. |  |  |  |
| 2 | Apologies for absence |  |  |  |
|  | Toby Neal and Ian Howe. |  |  |  |
| 3 | Appointment of Chair |  |  |  |
|  | It was confirmed that Mark Stilwell is the current Chair. | Appointment of Chair to be added to agenda for March meeting |  |  |
| 4 | Confirmation of Minutes of 24 July 2020 |  |  |  |
|  | The minutes were recorded as a true record. Review of Training Policy BS confirmed that the Learning Needs Analysis has been sent out for all to complete and return. | All to complete Learning Needs Analysis and return to Becky |  |  |
| 5 | Current Issues |  |  |  |
|  | WYPF will be taking over pension admin from 1 December. The project is on target and going to plan with no major problems. McCloud transitional protection scheme Currently in consultation and seeking views on proposals. Seeking Will affects members who were in service on or before 31 March 2012. The consultation proposes giving the choice between receiving legacy or the reformed 2015 scheme benefits. Consultation proposing to give the choice to immediately transfer across or have a deferred choice at the point the member retires. Members who have transferred to the 2015 scheme have been identified and will be monitoring those who are coming up for retirement during the transfer period. Both Service and FBU response is to go with deferred option which is in line with the Scheme Advisory Board. |  |  |  |
| 6 | Risk Register |  |  |  |
|  | Some of the higher level risks are beginning to be mitigated since having HS and team came on board. BS will update the risk register in December when the official transfer takes place. BS has added an extra risk relating to the impact of future court cases in line with minutes from last meeting. Discussion took place around the risks of moving to new pension schemes resulting from the McCloud remedy. | Action: BS to reflect in register the transfer of firefighters to correct pension scheme to reflect the McCloud remedy. | BS |  |
| 7 | Pension Fund Administrator Report – July 2020 |  |  |  |
|  | Benefit statements went out by deadline of 31 August. Leicestershire will provide GAD valuation information as too close to deadline for West Yorkshire to carry it out. |  |  |  |
| 8 | Annual Report to Policy and Strategy Committee |  |  |  |
|  | The annual report was approved for presentation to Policy and Strategy Committee. Due to Covid-19 restrictions, the report is going to Policy and Strategy Committee slightly later than usual. |  |  |  |
| 8 9 8 | Financial Position 31 March 2020 |  |  |  |
|  | The report was circulated to all for review. Contribution rate currently being revaluated by GAD. Employee contributions rate won’t be released until 2023. |  |  |  |
| 8 10 8 | Firefighter Pension Scheme Bulletin |  |  |  |
|  | The bulletin was circulated to all for review. Administration Strategy is currently linked to Leicestershire. BS will revise and bring to next meeting for review. | Action: BS to bring a revised Administration strategy to next meeting. | BS |  |
| 11 | Any Other Business |  |  |  |
|  | Should anyone have any training requirements, please contact BS/NL ahead of next meeting. |  |  |  |
| 12 | Next Meeting |  |  |  |
|  | 22 March 2021 at 2pm – location to be confirmed. |  |  |  |

Pension Board Meeting Actions (as at 9 October 2020)

|  | SMF Discussion Date | Subject | Commentary | Due Date | By Whom | Comp | Overdue | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 23 | 14/03/2018 | Link to Administrators page | A link to the Pension Administrator’s page to be added to MyNet so that the form can be accessed easily. EJ to send a copy to NL. |  | EJ/NL | 25/06/2019 |  |  |
| 31 | 13/03/2019 | Presentation on 2016 Valuation Results | BS to discuss with other scheme managers to establish their viewpoints and feedback the consensus to EJ |  | BS | 25/06/2019 |  |  |
| 32 | 13/03/2019 | Current Issues | BS to remove 2.1 for the next report |  | BS | 25/06/2019 |  |  |
| 33 | 13/03/2019 | Current Issues | BS to keep Board informed of the 27 cases |  | BS |  |  |  |
| 34 | 13/03/2019 | Risk Register | BS to bring the audit findings to the next board meeting | Next Board Meeting | BS | 25/06/2019 |  |  |
| 35 | 13/03/2019 | Risk Register | EJ will check on cyber security |  | EJ | 25/06/2019 |  |  |
| 36 | 13/03/2019 | Annual Report | Any comments on the report to be fedback to BS |  | All | 25/06/2019 |  |  |
| 37 | 25/06/2019 | Declarations of Potential Conflicts of Interest | All to return completed declaration of potential conflicts of interest form to BS |  | All |  |  |  |
| 38 | 24/10/2019 | Review of Training Policy | All to complete the learning needs analysis |  | All |  |  |  |
| 39 | 24/10/2019 | Firefighter Pension Scheme Bulletin | Any queries on the bulletin to contact BS |  | All | 09/07/2020 |  |  |
| 40 | 24/10/2019 | Firefighter Pension Scheme Bulletin | BS to add the changes in scoring to the risk register |  | All | 09/07/2020 |  |  |
| 42 | 09/07/2020 | Firefighter Pension Scheme Bulletin | BS to add the future court case potential costs to the risk register |  | BS | 09/10/2020 |  |  |
| 43 | 09/10/2020 | Risk Register | BS to add risk surrounding transfer of pension scheme on to risk register. |  | BS | 22/3/21 |  |  |
| 44 | 09/10/2020 | Administration Strategy | BS to bring a revised Administration Strategy to next meeting. | 22/03/2021 | BS |  |  |  |