Local Firefighter Pension Board

FIREFIGHTER’S PENSION RISK REGISTER

Report of the Scheme Manager

| Agenda Item No: | 7 |
| --- | --- |
| Date: | 23 May 2022 |
| Purpose of Report: |
| To update Board members on the current status of the Firefighter’s Pension Risk Register. |
| Recommendations: That Board members note the updated Risk Register attached at Appendix 1. |
| CONTACT OFFICER |
| Name : | Becky Smeathers, Scheme Manager |
| Tel : | 0115 967 0880 |
| Email : | becky.smeathers@notts-fire.gov.uk |
| 1. BACKGROUND |

  - The Pension Regulator recommends that the pension scheme manager must establish and operate adequate internal controls that enable them to manage the risks that relate to the scheme.  The scheme should also have a process to identify, evaluate and manage risks on an ongoing basis.

  - The Pension Risk Register is a key document to identify areas of risk, identifying appropriate actions to mitigate this risk and to manage the process.  The document is a live document, continually being updated and reviewed.

2. REPORT

Developments since last meeting

2.1	The current risk register is attached at Appendix 1.  Changes since the October meeting and updates to the risks are highlighted in grey on the risk register.

2.2 	The highest risk remains the McCloud age discrimination case following the Transitional Protections Pension Claims: Schedule 22 Appeal judgement which requires Fire Authorities to implement the remedy prior to updated legislation being passed.  Policy and Strategy Committee agreed continuation of implementation of Immediate Detriment in April 22 but the required amendments to legislation are not expected until October 23.

2.3	One risk has been removed from the register (Risk 10), which relates to the risk of interruption of service due to Covid-19 given that restrictions have now been lifted.  This will be kept under review should the situation change in the future.

2.4	The risks which score Very High on the Risk Matrix in Appendix 1 are identified in the table below:

| Risk Number | Risk | Comments |
| --- | --- | --- |
| 1,2, 12,18,19 | McCloud transitional protection remedy | Both the risk of disruption of service and additional costs remain a very high risk. This also impacts on several other risks, including the workload for the administrators once the remedy is agreed upon and communication with members. |
| 3 | Member data and records incomplete or inaccurate. | This risk remains at an elevated level until the payroll software has been updated to allow monthly transfer of data to WYPF. |
| 13 | Four Yearly Pension Scheme Valuation – Risk of increased contributions and affordability. | This follows the increase in employer contribution costs caused by the changes in the discount rates. The date of the next valuation is 31 March 2020. This could have a major impact on costs as it will need to reflect the McCloud judgement. For this reason, it may be some time before the results and likely impact are known. Any change in employer rates will take effect from April 2024. |
| 18 | Failure to interpret rules or legislation correctly. | This risk is linked to the McCloud remedy given that there is a lack of legislation and national guidance. |
| 19 | Communications with Members may not meet statutory requirements. | This has been left in the “very high risk” category due to the lack of national guidance regarding the age discrimination remedy. This makes it very difficult to accurately communicate with members. |

3. FINANCIAL IMPLICATIONS

Many of the risks identified in this report will have financial consequences.  Some of these are national issues and the Authority may receive additional funding to cover these costs.  Any unfunded costs will need to be met from either revenue budgets or General Fund reserves. Any financial implications for the Authority will be reported to the Finance and Resources Committee.

4. HUMAN RESOURCES AND LEARNING AND DEVELOPMENT IMPLICATIONS

There are human resources implications arising directly from this report, in that pension matters affect most employees. HR department staff are fully involved in pension issues to ensure that human resources implications are taken into account.

5. EQUALITY IMPACT ASSESSMENT

An equality impact assessment has not been carried out as this is not a new policy.

6. CRIME AND DISORDER IMPLICATIONS

There are no crime and disorder implications arising from this report.

7. LEGAL IMPLICATIONS

The Public Service Pensions Act 2013 introduced a framework for the governance and administration of public service pension schemes. This report aims to fulfil the requirement for Pension Board members to assist the Scheme Manager in ensuring that effective administration arrangements are in place.

8. RISK MANAGEMENT IMPLICATIONS

There are a number of risks relating to the firefighter pension schemes, and these have been presented to the Board in the form of a risk register. The Scheme Manager is responsible for ensuring that the risks identified are appropriately managed. All of the issues outlined in this report are being, or have been dealt with by close co-operation between the pension administration team and Officers.

9. RECOMMENDATIONS

That Board members note the content of this report.

10. BACKGROUND PAPERS FOR INSPECTION (OTHER THAN PUBLISHED DOCUMENTS)

None.

##### BECKY SMEATHERS

SCHEME MANAGER

Appendix 1

| Number | Risk | Level | Impact | Risk Score | Existing Controls | Revised Level | Revised Impact | Revised Score | Further Controls Required / Comments | Risk Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Operational Risks |  |  |  |  |  |  |  |  |  |
| 1 | McCloud Transitional Protection Arrangements discrimination case. Lack of national advice / direction or over complexity of new arrangements. Incorrect interpretation of advice / incorrect calculations of adjustments Administrators and NFRS staff unable to cope with increased workload. Unable to provide timely/ accurate advice to members. Transfer of firefighters to correct pension scheme to reflect the remedy. Lack of data to allow correct calculations to be made. | 5 | 5 | 25VH | Potential costs now estimated and continuation of payments approved by Policy and Strategy Committee in April 22. Attendance at relevant training/ information sharing events. Working closely with partnership organisations such as West Yorkshire Pension Fund and other regional fire services. New administrators have understanding and awareness of situation. Affected members have been identified and are being dealt with. | 5 | 5 | 25VH | Continued engagement at national level – both LGA and Fire Finance Network. Nationally procured legal advice being sought. Accurate Communication with members. | Scheme Manager |
| 2 | Incorrectly applied Tax Rules, including incorrect advice given to members. Increased Risk due to age discrimination remedy implementation Lack of advice from HMT | 5 | 5 | 25VH | Periodic national pension training organised by scheme advisory board. Attendance at training / conference events. Keeping up to date with information provided through LGA / Fire Finance Network and administration circulars. | 5 | 5 | 25VH | Awaiting advice / guidance from HMRC / Treasury LGA procuring legal advice. Scheme Advisory Board looking at developing common list of benefits to be included in pensionable pay. | Scheme Manager |
| 3 | Member data and records incomplete or inaccurate. | 3 | 4 | 12VH | Full review of records undertaken post transfer of pension administration from NCC to LCC. Pension benefit statements issued on annual basis. Errors in records rectified and identified. Reconciliation to HMRC records 2017. Reconciliation between payroll and Administrator records. Internal Pension Audits. Checks on data by new administrators as part of transfer. | 3 | 4 | 12VH | Introduction of monthly returns from NFRS (Iconnect) to reduce risk of data errors or missing data and reduce impact of year end work. This is being progressed. Improved recording of data within ITrent. Implement Data Improvement Plan once data audit complete. | Scheme Manager Pension Scheme Admin |
| 4 | Pension software supplier disruption. | 2 | 5 | 10H | Software suppliers involved with McCloud discussions. Agreement to update software prior to legislation changes | 2 | 5 | 10H |  | Scheme Manager |
| 5 | Impact of Matthews & O’Brien case on Modified Scheme - Pension calculations need to go back to start of service rather than current date of July 2000. Data unlikely to be available in order to make accurate calculations and estimations likely to be necessary. Difficulties in identifying all those affected Members. | 3 | 3 | 9H | Memorandum of Understanding agreed between Government, FBU and LGA March 22. Legislation to be drawn up to implement a Second Options Exercise. This is likely to take a further 18 months. New Pensions Officer to oversee process. | 3 | 3 | 9H | Data is in process of being reviewed and gaps identified. | Scheme Manager |
| 6 | Member data and records incomplete or inaccurate. | 3 | 4 | 12VH | Full review of records undertaken post transfer of pension administration from NCC to LCC. Pension benefit statements issued on annual basis. Errors in records rectified and identified. Reconciliation to HMRC records 2017. Reconciliation between payroll and Administrator records. Internal Pension Audits. Checks on data by new administrators as part of transfer. | 2 | 4 | 8H | Introduction of monthly returns from NFRS (Iconnect) to reduce risk of data errors or missing data and reduce impact of year end work. This is being progressed. Improved recording of data within ITrent. Implement Data Improvement Plan once data audit complete. | Scheme Manager |
| 7 | Administration process failure/ maladministration. Increased risk with additional workload related to age discrimination remedy and Matthews / O’Brien case. | 3 | 4 | 12VH | WYPF now taken over administration. WYPF larger organisation with better resilience. Regional quarterly client meetings to discuss current pension issues. National advice and guidance from Pensions Adviser at the Local Government Association. Completion and feedback from TPR Scheme Return. Pension Governance Audit judged as Substantial Assurance. Formal agreement in place with administrator to include SLA and performance indicators against defined criteria, which are reported to Pension Board. | 2 | 4 | 8H | Internal audit of pension administration. Monitoring of SLA Review of Pension Administration Strategy | Scheme Manager |
| 8 | New General Data Protection Regulation (GDPR) | 2 | 3 | 6M | Staff being provided with appropriate training Covered within organisation’s wider GDPR controls. Working with other Regional Fire Authorities to ensure compliance. Privacy Notice in place | 2 | 3 | 6M |  | Scheme Manager |
| 9 | Termination given by new administrators due to workload / risk etc | 2 | 5 | 10H | New administrators fully aware of additional workload resulting from current legal challenges and are currently taking on new clients. | 21 | 5 | 10H 5M | Keep under review. | Scheme Manager |
| 10 | Risk of interruption of service due to COVID-19 | 2 | 3 | 6M | Meetings moved to virtual platforms and streamed. LGA training has been moved to virtual platform. Internal functions and Pension Admin functions currently working well. | 1 | 3 | 3L | Continue to monitor situation due to increase in covid infections. | Scheme Manager |
| 11 | Operational disaster fire/flood for example. | 1 | 5 | 5M | Business continuity procedures in place for NFRS Pensions Administrator. Business continuity plans in place Finance and Payroll Team (NFRS). These were reviewed in March 2020. Business Continuity Plans for the administrators are embedded in their corporate plans. | 1 | 3 | 3M |  | Pensions Admin Manager Scheme Manager |
|  | Financial Risks |  |  |  |  |  |  |  |  |  |
| 12 | McCloud: Potential Costs of McCloud Remedy being implemented before legislation in place. Costs may escalate to fund additional resources for implementation and system development; Risk of fines / compensation if incorrect advice given due to complexity of the system. | 4 | 4 | 16VH | Exercise undertaken to identify those staff who may be affected and associated impact levels. Report considered by Policy and Strategy Committee April 22. Membership of Local Pension Board Effectiveness Committee – to gain knowledge and ability to influence national picture. Additional resources have been procured to assist with scheme management. | 4 | 4 | 16VH | Work ongoing regarding implementing the remedy. Working with LGA, local partners and Fire Finance Network | Scheme Manager |
| 13 | 4 Yearly Pension Scheme Valuation – Risk of increased contributions and affordability. | 4 | 4 | 16VH | LGA have sub group who work on behalf of authorities to challenge any assumptions made that will affect valuations. LGA have appointed independent Actuaries to verify figures and challenge GAD if necessary. Changes to cost control mechanism to be implemented from 2020 valuation to reduce risk of significant cost increases. This will not affect outcome of 2016 valuation. | 4 | 4 | 16VH | Future impact on Authority budgets will be included in spending review. The date of the next valuation is 31 March 2020. This may again have a major impact due to McCloud. Employer rates will not be increased until April 2024. | Scheme Manager |
| 14 | Pension Fund Accounting mistakes | 3 | 4 | 12VH | Checks undertaken by accountancy and HR of ill health and injury charges which has shown they are charged to the Authority, not the Pension fund. GMP checks have highlighted prior year errors that are in the process of being corrected. Internal audit reports provide substantial assurance. | 2 | 4 | 8H | Keep under review using national guidance, audits and reconciliations. | Scheme Manager |
| 15 | Excessive charges by NFRS Pension Administrators. | 2 | 4 | 8H | New administrators appointed on 5 year contract with option to extend. Costs could still escalate given additional McCloud work, although West Yorkshire Pension Fund represent several Fire Services, and costs will be spread across them all. | 2 | 4 | 8H | Monitor costs related to McCloud. Monitor risk of financial loss should maladministration occur. | Scheme Manager |
| 16 | Collection of Incorrect Employer Contributions | 2 | 3 | 6M | Ensure correct procedures in place – especially surrounding tapering between schemes. Received positive Internal Audit assessment. | 2 | 3 | 6M | Include in future audits. | Scheme Manager |
| 17 | Fraudulent behaviour, including members forgetting to provide updated information | 1 | 4 | 4M | NFRS Internal financial processes. Check incoming and outgoing scheme funds against schemes forecast – reconciliation process. Internal audit have reviewed processes as part of their pensions audit which was judged to provide substantial assurance. | 1 | 3 | 3M | Conduct regular fraud monitoring process of incoming contributions payments against the schedule of contributions. Consider periodic information check with retired members. | Scheme Manager |
|  | Governance, Regulatory and Compliance |  |  |  |  |  |  |  |  |  |
| 18 | Failure to interpret rules or legislation correctly. | 4 | 5 | 20VH | Regional quarterly client meetings to discuss current pension issues. National technical advice and guidance from LGA. Advice and guidance from administrators. Attendance at national training events. Advice and guidance from pension regulator. Policies and procedures in place. Formal IDRP process in place for addressing individual pension disputes LGA Bulletin to be reviewed by Pension Board. | 5 | 5 | 20VH | Complexity of age discrimination guidance and lack of legislation make this an increased risk. | Scheme Manager |
| 19 | Communications with Members may not meet statutory requirements. | 4 | 4 | 16VH | The Annual Benefits Statement is one form of communication, and this is already shown as a separate issue on the risk register. Information is sent to those members who are breaching or close to breaching the Annual Tax Allowance. Communications to starters, leavers and those whose circumstances change are generally good, with processes embedded. Communications with Members around McCloud case is undertaken in partnership with WYPF and other regional FRSs. | 3 | 4 | 12VH | Additional communication required due to ongoing age discrimination case. | Scheme Manager |
| 20 | Training and understanding of members of the pension board | 4 | 4 | 16VH | National training provided by LGA and CIPFA. Regional training on key topics. Training session undertaken as part 2 of each Pension Board. Training Register kept up to date. | 3 | 3 | 9H | Provide training to address knowledge gaps identified: on-going. Skills and knowledge audit of the Board and key staff. | Scheme Manager |
| 21 | Annual Benefits Statements to be issued by statutory deadline | 2 | 4 | 8H | Regular liaison between pension administrator and software supplier Data supplied by NFRS in accordance with template and subject to checking by pension administrator. ABS statutory deadline achieved for last 4 years. | 2 | 4 | 8H | Moving towards implementation of monthly inputting. Will need to be monitored with WYPF. Risk for 2020/21 remains due to delays in updating software to allow monthly inputting. | Scheme Manager |
| 22 | Impact of Future Court Cases. Risk of increased potential work load and costs. | 2 | 4 | 8H | Monitoring of national situation via LGA updates and training. Liaison with Scheme Administrators. | 2 | 4 | 8H |  | Scheme Manager |
| 23 | Cyber Risk | 2 | 4 | 8H | Fire Walls / ICT processes / accreditation Administrators have robust procedures in place. | 2 | 4 | 8H |  | Scheme Manager |
| 24 | High turnover of Board members | 2 | 3 | 6M | Ensure initial training available to new members to maintain knowledge of Board. | 2 | 3 | 6M |  | Scheme Manager |
| 25 | Creation of Joint Pension Board – impact on scheme governance / reputational risk | 2 | 2 | 4L | Working closely with Derbyshire and Leicestershire Pension Boards to ensure governance of individual scheme is not weakened through creation of joint board | 2 | 2 | 4L | This is on hold pending appointment of new pension administrators. | Pension Board |
| 26 | Systems failures | 2 | 4 | 8H | Back up and Business Continuity plans | 1 | 4 | 4M |  | Scheme Manager |
| 27 | Classification of pensionable allowances | 2 | 4 | 8H | All allowances were reviewed against Blackburn principles when initially paid. Attendance at LGA training seminar July 19. Internal Review of pensionable allowances July 19. | 1 | 4 | 4M |  | Scheme Manager |
| 28 | Potential conflict of interest for members of Pension Board. | 2 | 4 | 8H | Pension board members to declare any conflicts and potential conflicts of interest on appointment to the Board and on an ongoing basis. This is kept on a Conflict of Interest Register. Members of Pension Board to declare any potential conflict of interest at Pension Board meetings. Conflict of interest policy has been adopted by the Board Covered by Pension Governance Audit which provided substantial assurance. | 1 | 3 | 3M | Review and acceptance of reviewed Conflict of Interest Policy – October 2019 Board meeting. | Scheme Manager |

Risk Scoring Matrix

# Text boxes

Medium

Medium

Medium

Medium

Medium

Medium

Medium

High

High

High

High

High

Very High

Very High

Very High

Very High

Very High

Very High

Low

Low

Low

Low

Low

Low

Low

Impact

Negligible	         Moderate		      Severe

Minor	           Significant

1	           2	  3	     4	       5

1	        2		      3		  4		5

Negligible			Moderate		      Severe

Minor		           	        Significant

Likelihood